## Slide 1
Piscataqua River Bridge
SPS Corporate Management Meeting
April 11, 2019

## Slide 2: Agenda
Project Scope
Construction Schedule and Maintaining Traffic
Site Photos

## Slide 3: Project Purpose
Preventative maintenance
Improve traffic flow at peak volumes
Improve safety

## Slide 4: Who is Involved?

## Slide 5: Project Timeline
Project Advertised November 2018
Bid Opening January 2019
Project Awarded to SPS NE March 2019
Substantial Completion October 2021
Final Completion May 2022

## Slide 6: Project Scope

## Slide 7: Project Scope

## Slide 8: Project Scope
Traffic Control
Access to work locations
Asphalt wearing surface replacement
Bridge deck and substructure repairs
Joint replacement
Fascia & median barrier replacement

## Slide 9: Project Scope
Bridge drainage replacement
Zinc Anode Systems
Electrical system upgrade
Maine approach work to Exit 3 NB

## Slide 10: Existing Railing & Median Barrier

## Slide 11: New Fascia & Median Barrier

## Slide 12: Part-Time Shoulder Use

## Slide 13: Construction Scheduling & Maintaining Traffic

## Slide 14: Construction Schedule
Beginning in June 2019
Substantial Completion October 1, 2021
Contract Completion May 20, 2022
Substantial Completion Incentives
Contract Completion Incentives

## Slide 15: Proposed Construction Schedule
Southbound Fascia – 2019-2020
Northbound Fascia - 2020
NB & SB Median - 2021
Final Pave - Spring 2022

## Slide 16: Maintaining Traffic
“Peak” - 3 lanes open for summer traffic
  Daytime, Memorial Day to Columbus Day
  Work in shoulders w/ lane shifts
“Non-Peak” – 2 lanes open
  Daytime, Columbus Day to Memorial Day
  3 lane Incentives – NB on Fri/Sat and SB Sun
Nighttime extra lane closures: 7pm – 6am

## Slide 17
Non-Peak (Fascia Lane)
Peak (Fascia Shoulder)
Peak (Median Shoulder)
Non-Peak (Median Lane)

## Slide 18: Site Photos

## Slide 19: Site Photos

## Slide 20: Site Photos

## Slide 21: Site Photos

## Slide 22: Site Photos

## Slide 23: Site Photos

## Slide 24: Site Photos

## Slide 25: Site Photos

## Slide 26: Site Photos

## Slide 27: Site Photos

## Slide 28: Questions?